## Manuscript
PROJECT TITLE |  | Senior Citizen Management System
WBS NUMBER | TASK TITTLE | TASK OWNER | NAME | START DATE | DUE DATE | MAY |  |  |  | JUNE |  |  |  | JULY
[6 empty] | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
1 | Preliminary Pages | Project Manager | Alfanta | 2026-06-14 | 2026-06-17
1.1 | Title Page | Project Manager | Alfanta | 2026-06-14 | 2026-06-17
1.2 | Approval Sheet | Project Manager | Alfanta | 2026-06-14 | 2026-06-17
1.3 | Acknowledgement | Project Manager | Alfanta | 2026-06-14 | 2026-06-17
1.4 | Dedication | Project Manager | Alfanta | 2026-06-14 | 2026-06-17
1.5 | Table of Contents | Project Manager | Alfanta | 2026-06-14 | 2026-06-17
1.6 | List of Figures | Project Manager | Alfanta | 2026-06-14 | 2026-06-17
1.7 | List of Tables | Project Manager | Alfanta | 2026-06-14 | 2026-06-17
1.8 | List of Abbreviations / Acronyms | Project Manager | Alfanta | 2026-06-14 | 2026-06-17
1.9 | Executive Summary | Project Manager | Alfanta | 2026-06-14 | 2026-06-17
2 | Chapter I – Introduction | Documenter | Tangpos | 2026-06-14 | 2026-06-17
2.1 | Project Context | Project Manager | Alfanta | 2026-06-14 | 2026-06-17
2.2 | Purpose and Description | Documenter | Africano | 2026-06-14 | 2026-06-17
2.3 | Objectives of the System (General/Specific) | Documenter | Ababan | 2026-06-14 | 2026-06-17
2.4 | Scope and Limitation of the System | Documenter | Sarno | 2026-06-14 | 2026-06-17
2.5 | Definition of Terms | Documenter | Mondejar | 2026-06-14 | 2026-06-17
3 | Chapter II – Review of Related Literature and Systems | Data Analyst | Dela Cerna | 2026-06-14 | 2026-06-17
3.1 | Related Literature and Systems | Project Manager | Alfanta | 2026-06-14 | 2026-06-17 | bar: JUNE W4
3.2 | Synthesis | Project Manager | Alfanta | 2026-06-14 | 2026-06-17 | bar: JUNE W4
4 | Chapter III – Technical Foundation | Data Analyst | Dela Cerna | 2026-06-14 | 2026-06-17
4.1 | Organizational Structure | Data Analyst | Dela Cerna | 2026-06-14 | 2026-06-17
4.2 | Technical Environment | Developer | Paragat | 2026-06-14 | 2026-06-17
4.3 | Development Tools and Technologies | Developer | Paragat | 2026-06-14 | 2026-06-17
5 | Chapter IV – Methodology
5.1 | Research Approach | Documenter
5.2 | Software Development Methodology | System Analyst
5.3 | Project Management Plan | Project Manager
5.4 | Requirements Analysis and Documentation | System Analyst
5.5 | System Design | System Analyst
5.6 | Development and Testing Procedures | Developer
5.7 | Implementation Strategies | Developer
6 | Chapter V – Design of the Prototype
6.1 | Operational Framework | System Analyst
6.2 | User Interface Design | Developer
7 | Chapter VI – Results and Discussions
7.1 | Summary of Findings | Documenter
7.2 | Recommendations | Project Manager
Legend: | Izzy Alfanta
Jake Paragat
Arve Ian Sarno
Ivan Dela Cerna
Kent Jay A baban
Jemuel Africano
Melchor Mondejar
Jessa Tangpos

## Development
PROJECT TITLE |  | Senior Citizen Assistance System for Barangay Services
WBS NUMBER | TASK TITLE | TASK OWNER | NAME | START DATE | DUE DATE | SEPTEMBER 2026 |  |  |  | OCTOBER 2026 |  |  |  | NOVEMBER 2026
[6 empty] | 2026-09-07 | 2026-09-14 | 2026-09-21 | 2026-09-28 | 2026-10-05 | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23
1 | Planning and Design | Project Manager | Alfanta | 2026-09-07 | 2026-09-18 | bar: 2026-09-07 to 2026-11-23
1.1 | Requirements gathering and scope definition | Project Manager | Alfanta | 2026-09-07 | 2026-09-11 | bar: 2026-09-07
1.2 | Process mapping and database design | System Analyst | Dela Cerna | 2026-09-14 | 2026-09-18 | bar: 2026-09-14
1.3 | Interface wireframes and project setup | Developer | Paragat | 2026-09-07 | 2026-09-18 | bar: 2026-09-07 to 2026-09-14
2 | Core System | Project Manager | Alfanta | 2026-09-14 | 2026-10-09 | bar: 2026-09-07 to 2026-11-23
2.1 | Development environment and database implementation | Developer | Paragat | 2026-09-14 | 2026-09-18 | bar: 2026-09-14
2.2 | Authentication and role-based access | Developer | Paragat | 2026-09-21 | 2026-09-25 | bar: 2026-09-21
2.3 | Senior registration and profile management | Developer | Paragat | 2026-09-28 | 2026-10-02 | bar: 2026-09-28
2.4 | Administrator registration approval and ID review | Developer | Paragat | 2026-10-05 | 2026-10-09 | bar: 2026-10-05
3 | Barangay Service Features | Project Manager | Alfanta | 2026-10-05 | 2026-10-16 | bar: 2026-09-07 to 2026-11-23
3.1 | Assistance request workflow and status tracking | Developer | Paragat | 2026-10-05 | 2026-10-09 | bar: 2026-10-05
3.2 | Announcements and events management | Developer | Paragat | 2026-10-05 | 2026-10-09 | bar: 2026-10-05
3.3 | Senior portal dashboard and notifications | Developer | Paragat | 2026-10-12 | 2026-10-16 | bar: 2026-10-12
3.4 | SMS gateway integration and delivery logs | Developer | Paragat | 2026-10-12 | 2026-10-16 | bar: 2026-10-12
4 | Administration and Security | Project Manager | Alfanta | 2026-10-19 | 2026-10-30 | bar: 2026-09-07 to 2026-11-23
4.1 | Staff dashboard and senior records | Developer | Paragat | 2026-10-19 | 2026-10-23 | bar: 2026-10-19
4.2 | Reports, audit logs, settings, and backups | Developer | Paragat | 2026-10-19 | 2026-10-23 | bar: 2026-10-19
4.3 | Security hardening and access-control review | Developer | Paragat | 2026-10-26 | 2026-10-30 | bar: 2026-10-26
5 | Testing, Deployment, and Handover | Project Manager | Alfanta | 2026-11-02 | 2026-11-20 | bar: 2026-09-07 to 2026-11-23
5.1 | Integration and user-acceptance testing | Tester | Tangpos | 2026-11-02 | 2026-11-06 | bar: 2026-11-02
5.2 | Bug fixes and performance tuning | Developer | Paragat | 2026-11-09 | 2026-11-13 | bar: 2026-11-09
5.3 | Documentation, deployment, and staff orientation | Project Manager | Alfanta | 2026-11-16 | 2026-11-20 | bar: 2026-11-16
Legend: ■ Planned development period ¦ Schedule: 7 September – 20 November 2026 (12 weeks)